## Report
UID | Name | Start | Finish
1 | Release preparation | 2026-10-05 08:00 | 2026-10-16 17:00
2 | Define requirements | 2026-10-05 08:00 | 2026-10-05 17:00
3 | Architecture & interfaces | 2026-10-06 08:00 | 2026-10-07 12:00
4 | Zażółć — implementation | 2026-10-07 13:00 | 2026-10-09 12:00
5 | Integration tests | 2026-10-09 13:00 | 2026-10-12 12:00
6 | Accessibility review | 2026-10-12 13:00 | 2026-10-13 17:00
7 | Documentation | 2026-10-14 08:00 | 2026-10-15 17:00
8 | Release approval | 2026-10-16 08:00 | 2026-10-16 17:00
9 | Launch | 2026-10-16 17:00 | 2026-10-16 17:00

## Work hours
UID | Name | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16
1 | Release preparation | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8
2 | Define requirements | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Architecture & interfaces | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Zażółć — implementation | 0 | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Integration tests | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0
6 | Accessibility review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 0
7 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0
8 | Release approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
9 | Launch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Status and groups
UID | Name | Status | Group
1 | Release preparation | Summary; critical
2 | Define requirements | Task; critical
3 | Architecture & interfaces | Task; critical
4 | Zażółć — implementation | Task; critical
5 | Integration tests | Task; critical
6 | Accessibility review | Task; critical
7 | Documentation | Task; critical
8 | Release approval | Task; critical
9 | Launch | Task; critical

## Baseline dates
UID | Name | Baseline start | Baseline finish
1 | Release preparation
2 | Define requirements | 2026-10-05 08:00 | 2026-10-05 16:00
3 | Architecture & interfaces | 2026-10-06 08:00 | 2026-10-06 16:00
4 | Zażółć — implementation | 2026-10-07 08:00 | 2026-10-07 16:00
5 | Integration tests | 2026-10-08 08:00 | 2026-10-08 16:00
6 | Accessibility review | 2026-10-09 08:00 | 2026-10-09 16:00
7 | Documentation | 2026-10-10 08:00 | 2026-10-10 16:00
8 | Release approval | 2026-10-11 08:00 | 2026-10-11 16:00
9 | Launch | 2026-10-12 08:00 | 2026-10-12 16:00

## Dependencies
Predecessor UID | Successor UID | Type | Lag
2 | 3 | Finish to start (FS) | 0
3 | 4 | Finish to start (FS) | 0
4 | 5 | Finish to start (FS) | 0
5 | 6 | Finish to start (FS) | 0
6 | 7 | Finish to start (FS) | 0
7 | 8 | Finish to start (FS) | 0
8 | 9 | Finish to start (FS) | 0