Delivery plan · Łódź

Task usage

| UID | Name | Start | Finish |
| --- | --- | --- | --- |
| 1 | Release preparation | 2026-10-05 08:00 | 2026-10-16 17:00 |
| 2 | Define requirements | 2026-10-05 08:00 | 2026-10-05 17:00 |
| 3 | Architecture & interfaces | 2026-10-06 08:00 | 2026-10-07 12:00 |
| 4 | Zażółć — implementation | 2026-10-07 13:00 | 2026-10-09 12:00 |
| 5 | Integration tests | 2026-10-09 13:00 | 2026-10-12 12:00 |
| 6 | Accessibility review | 2026-10-12 13:00 | 2026-10-13 17:00 |
| 7 | Documentation | 2026-10-14 08:00 | 2026-10-15 17:00 |
| 8 | Release approval | 2026-10-16 08:00 | 2026-10-16 17:00 |
| 9 | Launch | 2026-10-16 17:00 | 2026-10-16 17:00 |

Work hours · 2026-10-05

| UID / Name | 05 Oct 26 | 06 Oct 26 | 07 Oct 26 | 08 Oct 26 | 09 Oct 26 |
| --- | --- | --- | --- | --- | --- |
| 1 / Release preparation | 8 | 8 | 8 | 8 | 8 |
| 2 / Define requirements | 8 | 0 | 0 | 0 | 0 |
| 3 / Architecture & interfaces | 0 | 8 | 4 | 0 | 0 |
| 4 / Zażółć — implementation | 0 | 0 | 4 | 8 | 4 |
| 5 / Integration tests | 0 | 0 | 0 | 0 | 4 |
| 6 / Accessibility review | 0 | 0 | 0 | 0 | 0 |
| 7 / Documentation | 0 | 0 | 0 | 0 | 0 |
| 8 / Release approval | 0 | 0 | 0 | 0 | 0 |
| 9 / Launch | 0 | 0 | 0 | 0 | 0 |

Work hours · 2026-10-10

| UID / Name | 10 Oct 26 | 11 Oct 26 | 12 Oct 26 | 13 Oct 26 | 14 Oct 26 |
| --- | --- | --- | --- | --- | --- |
| 1 / Release preparation | 0 | 0 | 8 | 8 | 8 |
| 2 / Define requirements | 0 | 0 | 0 | 0 | 0 |
| 3 / Architecture & interfaces | 0 | 0 | 0 | 0 | 0 |
| 4 / Zażółć — implementation | 0 | 0 | 0 | 0 | 0 |
| 5 / Integration tests | 0 | 0 | 4 | 0 | 0 |
| 6 / Accessibility review | 0 | 0 | 4 | 8 | 0 |
| 7 / Documentation | 0 | 0 | 0 | 0 | 8 |
| 8 / Release approval | 0 | 0 | 0 | 0 | 0 |
| 9 / Launch | 0 | 0 | 0 | 0 | 0 |

Work hours · 2026-10-15

| UID / Name | 15 Oct 26 | 16 Oct 26 |
| --- | --- | --- |
| 1 / Release preparation | 8 | 8 |
| 2 / Define requirements | 0 | 0 |
| 3 / Architecture & interfaces | 0 | 0 |
| 4 / Zażółć — implementation | 0 | 0 |
| 5 / Integration tests | 0 | 0 |
| 6 / Accessibility review | 0 | 0 |
| 7 / Documentation | 8 | 0 |
| 8 / Release approval | 0 | 8 |
| 9 / Launch | 0 | 0 |

Status and groups

| UID | Name | Status | Group |
| --- | --- | --- | --- |
| 1 | Release preparation | Summary; critical |  |
| 2 | Define requirements | Task; critical |  |
| 3 | Architecture & interfaces | Task; critical |  |
| 4 | Zażółć — implementation | Task; critical |  |
| 5 | Integration tests | Task; critical |  |
| 6 | Accessibility review | Task; critical |  |
| 7 | Documentation | Task; critical |  |
| 8 | Release approval | Task; critical |  |
| 9 | Launch | Task; critical |  |

Baseline dates

| UID | Name | Baseline start | Baseline finish |
| --- | --- | --- | --- |
| 1 | Release preparation |  |  |
| 2 | Define requirements | 2026-10-05 08:00 | 2026-10-05 16:00 |
| 3 | Architecture & interfaces | 2026-10-06 08:00 | 2026-10-06 16:00 |
| 4 | Zażółć — implementation | 2026-10-07 08:00 | 2026-10-07 16:00 |
| 5 | Integration tests | 2026-10-08 08:00 | 2026-10-08 16:00 |
| 6 | Accessibility review | 2026-10-09 08:00 | 2026-10-09 16:00 |
| 7 | Documentation | 2026-10-10 08:00 | 2026-10-10 16:00 |
| 8 | Release approval | 2026-10-11 08:00 | 2026-10-11 16:00 |
| 9 | Launch | 2026-10-12 08:00 | 2026-10-12 16:00 |

Dependencies

| Predecessor UID | Successor UID | Type | Lag |
| --- | --- | --- | --- |
| 2 | 3 | Finish to start (FS) | 0 |
| 3 | 4 | Finish to start (FS) | 0 |
| 4 | 5 | Finish to start (FS) | 0 |
| 5 | 6 | Finish to start (FS) | 0 |
| 6 | 7 | Finish to start (FS) | 0 |
| 7 | 8 | Finish to start (FS) | 0 |
| 8 | 9 | Finish to start (FS) | 0 |