Platform release · delivery plan

Gantt

| UID | Name |
| --- | --- |
| 1 | Discovery & scope |
| 2 | API design |
| 3 | Interface design |
| 4 | Data migration plan |
| 5 | Build & integrate |
| 6 | Migration rehearsal |
| 7 | Acceptance & launch readiness |
| 8 | Release |

Status and groups

| UID | Name | Status | Group |
| --- | --- | --- | --- |
| 1 | Discovery & scope | Task; critical |  |
| 2 | API design | Task; critical |  |
| 3 | Interface design | Task; critical |  |
| 4 | Data migration plan | Task |  |
| 5 | Build & integrate | Task; critical |  |
| 6 | Migration rehearsal | Task |  |
| 7 | Acceptance & launch readiness | Task; critical |  |
| 8 | Release | Task; critical |  |

Dependencies

| Predecessor UID | Successor UID | Type | Lag |
| --- | --- | --- | --- |
| 1 | 2 | Finish to start (FS) | 0 |
| 1 | 3 | Finish to start (FS) | 0 |
| 1 | 4 | Finish to start (FS) | 0 |
| 2 | 5 | Finish to start (FS) | 0 |
| 3 | 5 | Finish to start (FS) | 0 |
| 4 | 6 | Finish to start (FS) | 0 |
| 5 | 7 | Finish to start (FS) | 0 |
| 6 | 7 | Finish to start (FS) | 0 |
| 7 | 8 | Finish to start (FS) | 0 |