## Slide 1
Delivery plan · Łódź
Task usage
UID | Name | Start | Finish
1 | Release preparation | 2026-10-05 08:00 | 2026-10-16 17:00
2 | Define requirements | 2026-10-05 08:00 | 2026-10-05 17:00
3 | Architecture & interfaces | 2026-10-06 08:00 | 2026-10-07 12:00
4 | Zażółć — implementation | 2026-10-07 13:00 | 2026-10-09 12:00
5 | Integration tests | 2026-10-09 13:00 | 2026-10-12 12:00
6 | Accessibility review | 2026-10-12 13:00 | 2026-10-13 17:00
7 | Documentation | 2026-10-14 08:00 | 2026-10-15 17:00
8 | Release approval | 2026-10-16 08:00 | 2026-10-16 17:00
9 | Launch | 2026-10-16 17:00 | 2026-10-16 17:00
Notes: Editable report data. Source revision 152. TaskUsage

## Slide 2
Delivery plan · Łódź
Work hours · 2026-10-05
UID / Name | 05 Oct 26 | 06 Oct 26 | 07 Oct 26 | 08 Oct 26 | 09 Oct 26
1 / Release preparation | 8 | 8 | 8 | 8 | 8
2 / Define requirements | 8 | 0 | 0 | 0 | 0
3 / Architecture & interfaces | 0 | 8 | 4 | 0 | 0
4 / Zażółć — implementation | 0 | 0 | 4 | 8 | 4
5 / Integration tests | 0 | 0 | 0 | 0 | 4
6 / Accessibility review | 0 | 0 | 0 | 0 | 0
7 / Documentation | 0 | 0 | 0 | 0 | 0
8 / Release approval | 0 | 0 | 0 | 0 | 0
9 / Launch | 0 | 0 | 0 | 0 | 0
Notes: Editable report data. Source revision 152. TaskUsage

## Slide 3
Delivery plan · Łódź
Work hours · 2026-10-10
UID / Name | 10 Oct 26 | 11 Oct 26 | 12 Oct 26 | 13 Oct 26 | 14 Oct 26
1 / Release preparation | 0 | 0 | 8 | 8 | 8
2 / Define requirements | 0 | 0 | 0 | 0 | 0
3 / Architecture & interfaces | 0 | 0 | 0 | 0 | 0
4 / Zażółć — implementation | 0 | 0 | 0 | 0 | 0
5 / Integration tests | 0 | 0 | 4 | 0 | 0
6 / Accessibility review | 0 | 0 | 4 | 8 | 0
7 / Documentation | 0 | 0 | 0 | 0 | 8
8 / Release approval | 0 | 0 | 0 | 0 | 0
9 / Launch | 0 | 0 | 0 | 0 | 0
Notes: Editable report data. Source revision 152. TaskUsage

## Slide 4
Delivery plan · Łódź
Work hours · 2026-10-15
UID / Name | 15 Oct 26 | 16 Oct 26
1 / Release preparation | 8 | 8
2 / Define requirements | 0 | 0
3 / Architecture & interfaces | 0 | 0
4 / Zażółć — implementation | 0 | 0
5 / Integration tests | 0 | 0
6 / Accessibility review | 0 | 0
7 / Documentation | 8 | 0
8 / Release approval | 0 | 8
9 / Launch | 0 | 0
Notes: Editable report data. Source revision 152. TaskUsage

## Slide 5
Delivery plan · Łódź
Status and groups
UID | Name | Status | Group
1 | Release preparation | Summary; critical | 
2 | Define requirements | Task; critical | 
3 | Architecture & interfaces | Task; critical | 
4 | Zażółć — implementation | Task; critical | 
5 | Integration tests | Task; critical | 
6 | Accessibility review | Task; critical | 
7 | Documentation | Task; critical | 
8 | Release approval | Task; critical | 
9 | Launch | Task; critical | 
Notes: Editable report data. Source revision 152. TaskUsage

## Slide 6
Delivery plan · Łódź
Baseline dates
UID | Name | Baseline start | Baseline finish
1 | Release preparation |  | 
2 | Define requirements | 2026-10-05 08:00 | 2026-10-05 16:00
3 | Architecture & interfaces | 2026-10-06 08:00 | 2026-10-06 16:00
4 | Zażółć — implementation | 2026-10-07 08:00 | 2026-10-07 16:00
5 | Integration tests | 2026-10-08 08:00 | 2026-10-08 16:00
6 | Accessibility review | 2026-10-09 08:00 | 2026-10-09 16:00
7 | Documentation | 2026-10-10 08:00 | 2026-10-10 16:00
8 | Release approval | 2026-10-11 08:00 | 2026-10-11 16:00
9 | Launch | 2026-10-12 08:00 | 2026-10-12 16:00
Notes: Editable report data. Source revision 152. TaskUsage

## Slide 7
Delivery plan · Łódź
Dependencies
Predecessor UID | Successor UID | Type | Lag
2 | 3 | Finish to start (FS) | 0
3 | 4 | Finish to start (FS) | 0
4 | 5 | Finish to start (FS) | 0
5 | 6 | Finish to start (FS) | 0
6 | 7 | Finish to start (FS) | 0
7 | 8 | Finish to start (FS) | 0
8 | 9 | Finish to start (FS) | 0
Notes: Editable report data. Source revision 152. TaskUsage